To Do Checklist after topic/Speaker has been selected:

Before Event

Secure speaker – verbal agreement

Confirmation letter

Contract?

Assist with travel arrangements

Book hotel for speaker, if needed

Secure Hotel

Sign Agreement/Contract

Obtain Insurance Certificate (form attached)

Communicate the speaker’s audio visual requirements

Select Menu

Secure a Sponsor – verbal agreement

Confirmation letter

Contract?

Obtain advertising for newsletter

Forward ACA NJ members mailing list (Mary Ellen)

Registration

Establish pricing

Obtain directions to event

Create registration form, copy and distribute

Snail mail

e-mail

website posting

Registration Processing (Section Exec.)

Process payments credit/check

Create name badges

Confirmation e-mails (e.g. “Your registration has been received…..)

Marketing

Save the Date postcards/flyer

E-mail Blasts to members

Newsletter article

Press Releases

E-mail copies of registration forms to Keystone and NY Executives (Mary Ellen)

Decorations (optional)

Door prizes

Evaluation Form

Design, copy, distribute, collect and culminate the feedback

Program Agenda

Design and copy

Payments

Arrange two weeks in advance for Section Treasurer to cut the checks needed for payments day of the event.

During the Event

Set-up/Clean up

Greeters - door

Working the registration table

Announcements/Introductions

After the Event

Thank you letters to vendors, volunteers, etc.

American Camp Association, 2008